## Timeline
Breakfast Program Implementation Timeline
School: ______________________________________
4-6 Months Prior to Kick-Off |  | Due Date | Complete
Conduct Principal Survey to determine target school(s)
Conduct student & parent surveys/focus groups
Determine "best fit" program type for school
Discuss program with nutrition staff
Convince stakeholders (administration/principals/teachers/custodians)
Identify challenges/solutions (including equipment needs)
Develop timeline for implementation
3 Months Prior to Kick-Off
Meet with students to identify menu items & menu plan
Contact your vendors for free taste test samples
Order new equipment if needed
Secure approval from State
2 Months Prior to Kick-Off
Present new program at nutrition staff meeting
Present new program at teachers/school staff meeting
Plan Kick-Off celebration
1 Month Prior to Kick-Off
Get new equipment in place
Order supplies needed for Kick-Off celebration
Place announcements in school and local papers
Have staff practice with new equipment and menu
Send parents informational flyers
2 Weeks Prior to Kick-Off
Send menu home to parents
Send principal & teachers program information & ways to support
Test your procedures to work out any kinks
1 Week Prior to Kick-Off
Start with pre-Kick-Off PA announcements
Decorate for Kick-Off celebration
Send final reminder flyer home to parents
Send Kick-Off press release to local media (1 to 2 days before)
1 Week After Kick-Off
Send post-press release with pictures to local media
Solicit initial feedback from nutrition staff, custodian & teachers
Make necessary adjustments based on initial feedback
1-2 Months After Kick-Off
Solicit continued feedback from nutrition staff, custodians & teachers
Survey parents & students for comments & feedback
Continue to make modifications based on feedback